## Tasks Log
When |  |  |  | What |  | Who
Date | Time |  | Time Spent | Task | Details | Name | Comments
| Start | End | (hours)
Iteration 0 Starts - January 15th, 2016
(Bailey & Matt are out of town)
2016-01-15 | 14:30 | 17:30 | 3 hours | Interview | - Set up all necessary equipments (camera, audio, ...) for the interview, co-interviewed customer | Paul
[5 empty] | - Interviewed customer | Faye
[5 empty] | - Co-interviewed customer + wrote down user stories | LAM
|  |  | 1 hour | Vision statement | - Wrote vision statement | Paul
|  |  | 2 hours | Interview video | - Edit the video | Paul
2016-01-20 |  |  | 1 hour | User stories | - Scanned and formatted all of user stories | LAM
Iteration 1 Starts - February 1st, 2016
2016-02-03 | 14:30 | 17:15 | 2.75 hours | Setup Git | Resolved Git and build issues; Had members fork off of the main repo; Began merge testing | Matt
2016-02-10 | 14:30 | 17:30 | 3 hours | Setup Git cnt'd | Continued setting up Git; Made Git path to proper area for VC; Had all members fork the repo; | Matt
2016-02-17 | 2:30 | 18:00 | 3.75 hours | Resolved merge conflicts | Resolved merge conflicts; Added buttons for adding and deleting items(mipmap vs. drawable); All team members have upstream branches off of master; More Git discussions, using Git shell vs. Github for Windows vs. built-in Android studio | Matt
|  |  | 1 hour | Model | - Created models: TaskListManager, TaskList, TaskItem | Faye
|  |  | 3 hours | User Interface | - activity_task_list and list_item layout | XIRAN
2016-02-19 |  |  | 4 hours | Database Model | - Added DB model/schema and addTask | Paul | See add-list-item on upstream for commits
2016-02-20 |  |  | 6 hours | Database Model | - Model refinement, ArrayAdaptor onboarding | Paul | Custom ArrayAdaptor required for ListView
2016-02-21 |  |  | 4 hours | Check-off Item | - give task item a checkbox | Bailey | working on local branch check_off_item
2016-02-21 |  |  | 8 hours | Add-Item | - ArrayAdaptor completed, add functionality completed | Paul | Work missing unit tests only at this point
2016-02-21 |  |  | 4 hours | Delete-item | -delete task item from a database and a list | LAM | working on local branch lamdoan-delete-task-lits-item
2016-02-22 |  |  | 4 hours | Testing |  | Matt
Iteration 2 Starts - February 29th, 2016
2016-03-04 |  |  | 8 hours | Add Task Fix | Add Task: clicking outside of the edittext fails to save | Paul | branch: task-item-add-fixes
2016-03-05 |  |  | 3hours | Alarms | Research on alarms | Xiran
2016-03-09 |  |  | 1 hour | Delete-item | Finalized removeTask() method | LAM | working on local branch lamdoan-delete-task-lits-item
2016-03-10 | 19:30 | 3:00 | 7.5 hours | Add Alarm | Allowing user to add alarm for each task | Bailey | Researching and implementing alarms on local branch
2016-03-10 |  |  | 8 hours | Alarms | Researched how to implementing alarms | LAM
2016-03-10 |  |  | 1 hour | Delete-item | Finalized removeTask() method and got it to work -> Working for real this time | LAM | working on local branch lamdoan-delete-task-lits-item
2016-03-11 |  |  | 6 hours | Priorities | Reaseached and implemented spinners on local branch | LAM
2016-03-11 | 22:30 | 3:00 | 4.5 hours | Item Priorities | Changing priority ranking of an individual item | Bailey | Researching spinner objects for priority implementation
2016-03-11 |  |  | 1 hour | Item Priorities | Draw user interface for Priority User Story | Faye
2016-03-11 | 21:00 | 4:00 | 7 hours | Priorities | Implementing UI and Class for prirority spinner | Xiran
2016-03-12 | 22:00 | 4:00 | 6 hours | Item Priorities | implementing spinner for item priorities | Bailey
2016-03-12 |  |  | 4 hours | Priorities | Reaseached how to fix bug (The program will crash while editing task and clicking Delete task) | LAM
2016-03-12 |  |  | 3 hours | Priorities DB | Structure and database implementation for priorities | Paul | Please see https://github.com/DotFreelance/To-Do-Bot/wiki/Paul-J:-Changelog
2016-03-13 |  |  | 2 hours | Priorities | Trying to fix the resolution for the priorities pictures | Faye
2016-03-13 | 15:00 | 17:00 | 2 hours | Item Priorities | Setting item piorities and organizing items based on priorites | Bailey
2016-03-13 |  |  | 2 hours | Priorities cleanup | Priorities cleanup: fixed mipmaps for priorities, fixed bugs | Paul | Please see https://github.com/DotFreelance/To-Do-Bot/wiki/Paul-J:-Changelog
2016-03-14 |  |  | 1.5 hours | Testing | Finished leftover testing from iteration 1 | Matt
Iteration 3 Starts - March 14th, 2016
2016-03-14 |  |  | 1 hour | Priority Testing | Implemented testing for "Priority" | Faye & LAM
2016-03-16 |  |  | 2 hours | Alarms | Set up basic alarms | Matt
2016-03-25 | 6 hours per day |  | 24 hours | Iteration 3 Set up | Created and fixed UI for iteration 3 Cleaned up some unecessary codes Fixed and added some codes in order for it to work with the new UI Added more columns into the database | LAM
2016-03-26
2016-03-27
2016-03-28 | 3 hours per day
2016-03-29
2016-03-30 |  |  | 6 hours | Bugs | Edited several string values to make more sense Modified the layout of the Add Task to use only buttons for the alarm time Added a fix for the soft keyboard not showing when we enter the new task activity Added a fix for the cancel button crashing the app Added a fix for the multi-line description acting weird | Paul
2016-03-30 |  |  | 2 hours | Bugs | Added a fix for the soft keyboard not showing when we enter the new task activity Added a fix for the cancel button crashing the app | LAM | Working on the same bug as with Paul
2016-04-01 |  |  | 8 hours | Widgets, Pictures | Research how to implement pics, and widgets | Bailey
2016-04-01 |  |  | 1.5 hours | Categories | Setting up basic UI and codes for categories | LAM | Working on local branch lamdoan-categoryBasic
2016-04-03 |  |  | 8 hours | Categories, Alarms, Widgets, Pictures | Wrote codes and fixed UI for categories, alarms, widgets, and pictures user stories | LAM
2016-04-04 |  |  | 6 hours |  |  | LAM, Faye, Xiran | Working together and commited as one using Lam's laptop
2016-04-04 |  |  | 5 hours | Alarms | Fixed alarm codes, set sounds and notifications | Xiran | Had trouble with Github, using Lam's laptop to commit
2016-04-07 |  |  | 2 hours | Code smells | Remove duplicate methods, create a new class extended the dupilcate one | Faye | Had trouble with Github, using Lam's laptop to commit
2016-04-08 |  |  | 2 hours | BUGS | Added low priorities, removed uneccesary files, fixed widgets, changed song | LAM
2016-04-10 |  |  | 2 hours | Code smells | Fixed Category Constructor, and DivideItemDecorator | Faye
2016-04-11 |  |  | 3 hours | Final code smells | Fixed overall code smells | Faye
2016-04-11 |  |  | 4 hours | Architecture design | Finalized architecture design | Faye

## Meetings Log
When |  |  | Where | What | Who | [5 empty] | Attendance record
Date | Time |  | Location | Description | Attendees | [5 empty] | # Meetings: |  | 21
| Start | End |  |  | Faye | Paul | Lam | Xiran | Bailey | Matt | Member | Record | Percentage
2016-01-11 | 14:30 | 15:30 | E2 tables | - Set up Slack and Asana | x | x |  |  | x |  | Faye | 19 | 90.48%
|  |  |  | - Planned the next meeting | [6 empty] | Paul | 19 | 90.48%
[11 empty] | Lam | 19 | 90.48%
2016-01-13 | 14:30 | 16:00 | E2 tables | - Came up with ideas for the apps: to-do list or expense tracking | x | x | x | x |  |  | Xiran | 18 | 85.71%
|  |  |  | - Looked for potential customers | [6 empty] | Bailey | 18 | 85.71%
|  |  |  | - Brainstormed some interview questions for Friday interview | [6 empty] | Matt | 7 | 33.33%
2016-01-15 | 14:30 | 17:30 | E3-362D (Library group study room) | - Met the customer | x | x | x | x
- Discussed the project with customer and the customer chose To-do List
- Practiced going over some questions with customer before filiming several times
- Filmed a 20-mins interview video
- Wrote down some user stories while interviewing.
- Discussed the priority for each user story with a customer
2015-01-20 | 14:30 | 17:30 | E3-362D | - Planned and organized user stories | x | x | x | x | x | x
- Estimated the cost of developing each story
2015-01-22 | 14:30 | 17:15 | E3-362D | - Finalized iteration 0 | x | x | x | x | x
- Assigned tasks to each member.
2016-02-03 | 14:30 | 17:15 | E3-362D | - Resolved GitHub issues, resolved build issues, and got everybody on github | x | x | x | x | x
- Made all group members create a fork off of the main project.
- Started testing of merging project together.
- Resolved issues with repo's, deleted all forks and reforked and recloned our project
2016-02-05 | 14:30 | 17:15 | E3-362D | - Solved possible conflicts within Github | x | x |  | x | x | x
2016-02-10 | 14:30 | 17:15 | E3-362D | - Got version control to work for the group | x | x | x | x | x | x
- Made Git path to the proper area for version control
- Set up forks for all group members
2016-02-12 | 14:30 | 17:15 | E3-362D | - Solved possible conflicts within Github | x |  | x | x | x | x
2016-02-17 | 14:30 | 18:00 | E3-362D | - Got all conflicts with merging sorted. | x | x | x | x | x
- Added button images for delete and add items (in a mipmap vs drawable)
- All team members have their own branches off the main upstream (root) branch
- Discussed more about git, and how we’re going to implement version control
(just using the Git Shell vs using Android Studio’s built in version control).
2016-02-22 | 14:30 | 17:30 | E3-362C | - Finalized iteration 1 | x | x | x |  | x
- Added the architecture diagram to the upstream
- Merge all of the possible finished code from different branches into the upstream
2016-02-24 | 14:30 | 17:30 | E3-362D | - Merged check_off_item branch and lamdoan-delete-task-lits-item branch with master branch |  | x | x | x | x | x
- Looked for some potential bugs
2016-02-29 | 14:30 | 17:30 | Room 223A (Science Library) | - Looked through over iteration 2 | x | x | x |  | x
2016-03-09 | 14:30 | 17:30 | Room 360 (Science Library) | - Revised planning for iteration 2 |  | x | x | x | x
- Debugged bugs and assigned them for appropriate people to fix
- Chose new user story (Alarms) to implement and divide sub-tasks to each members
- Came up with a new UI for iteration 2
- Got removeTask() to work properly
2016-03-11 | 14:30 | 17:30 | E3-362D | - Discussed how to implement DatePicker and Alarms | x | x | x | x | x
- Researched how to implement Alarms
- Changed plan: implementing Priorities instead of Alamrs
- Came up with new UI for priorities
2016-03-14 | 14:30 | 17:30 | Room 223A | - Finished off iteration 2 | x | x | x | x | x
- Wrote testing for Priority
2016-03-23 | 14:30 | 17:30 | Room 223A | - Prepared for seminar | x |  | x | x | x
2016-03-28 | 14:30 | 17:30 | Room 360 | - Prepared for seminar | x | x | x | x | x
2016-03-30 | 14:30 | 17:30 | Room 360 | - Prepared for seminar (We had to refilm since the video was broken) | x | x | x | x
2016-04-01 | 10:15 | 10:30 | Engineering lounge | - Quick meeting to plan for iteration 3 | x | x | x | x | x | x
2016-04-03 | 10:30 | 11:30 | Room 360 | - Finalize iteration 3 | x | x | x | x | x | x